## Estimation
Subtask | Guesses | [5 empty] | Time estimation
| Best case |  | Most likely |  | Worst case |  | EE (sub-task) |  | SD (sub-task)
Analysis | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 20
Design / implementation | 3 | 0 | 6 | 0 | 12 | 0 | 6 | 30 | 1 | 30
Testing | 2 | 30 | 5 | 0 | 10 | 0 | 5 | 25 | 1 | 15
Notes: risk: 2 standard deviations; distribution used: PERT Read more: https://en.wikipedia.org/wiki/Three-point_estimation |  |  |  |  | EE (task) / SD (task) |  | 12 | 55 | 2 | 0
[5 empty] | E (task) |  | 16 | 55 | 0 | 0
Tracker
TIME ESTIMATION > Subtask: * Analysis: 1h0min * Design / Implementation: 6h30min * Testing: 5h25min > EE: 12h55min > E: 16h55min > Risk: 31%
Compute
Reset

## Tracking
Input | [7 empty] | Output: balancing summary | [6 empty] | Output: distributed across days
Ticket |  |  | Timestamp |  |  |  |  | Ticket | Time | [5 empty] | Ticket | Tracker
Name | E |  | Day | Start |  | End |  |  | Real |  | Fake |  | Total |  |  | Day | Time
0125391: [T] [AS] Review and implement 'abbreviations list' more user friendly | 13 | 0 | Mon | 10 | 13 | 11 | 42 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | 24 | 40 | 8 | 50 | 33 | 30 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Mon | 8 | 0
|  |  |  | 12 | 5 | 13 | 39 | 0124910: [t] chapters deleted with non-deleted questions | 1 | 45 | 3 | 5 | 4 | 50 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Tue | 8 | 0
|  |  |  | 14 | 35 | 15 | 32 | 0125392: [t] [as] end of chapter improvements | 0 | 15 | 0 | -5 | 0 | 10 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Wed | 8 | 0
0124910: [T] Chapters deleted with non-deleted questions | 2 | 30 |  | 15 | 48 | 17 | 33 | team meeting | 1 | 25 | 0 | 5 | 1 | 30 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Thu | 8 | 0
0125392: [T] [AS] End of Chapter improvements |  |  | Tue | 9 | 41 | 9 | 57 | TOTAL | 28 | 5 | 11 | 55 | 40 | 0 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Fri | 1 | 30
0125391: [T] [AS] Review and implement 'abbreviations list' more user friendly |  |  |  | 10 | 9 | 10 | 49 | [7 empty] | 0124910: [t] chapters deleted with non-deleted questions | Fri | 4 | 50
|  |  |  | 11 | 0 | 12 | 15 | [7 empty] | 0125392: [t] [as] end of chapter improvements | Fri | 0 | 10
|  |  |  | 12 | 30 | 13 | 45 | [7 empty] | team meeting | Fri | 1 | 30
|  |  |  | 14 | 40 | 14 | 53 | [7 empty] | TOTAL | Mon-Fri | 40 | 0
Team meeting | 0 | 25 |  | 14 | 55 | 16 | 22
0125391: [T] [AS] Review and implement 'abbreviations list' more user friendly |  |  |  | 16 | 44 | 17 | 10
|  |  | Wed | 10 | 30 | 13 | 10
|  |  |  | 14 | 0 | 15 | 38
|  |  |  | 16 | 1 | 16 | 36
|  |  |  | 16 | 45 | 17 | 30
|  |  |  | 17 | 44 | 18 | 0
|  |  | Thu | 9 | 50 | 11 | 15
|  |  |  | 11 | 26 | 12 | 14
|  |  |  | 12 | 25 | 13 | 42
|  |  |  | 14 | 33 | 16 | 25
|  |  | Fri | 10 | 5 | 12 | 5
|  |  |  | 12 | 23 | 13 | 39
|  |  |  | 14 | 30 | 15 | 47
|  |  |  | 16 | 8 | 17 | 10
Compute
Reset

## __OpenSolver__ (hidden)
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?

## Tracking-Week17-2025
TODO: export historical tracking data with one button
Input | [7 empty] | Output: balancing summary | [6 empty] | Output: distributed across days
Ticket |  |  | Timestamp |  |  |  |  | Ticket | Time | [5 empty] | Ticket | Tracker
Name | E |  | Day | Start |  | End |  |  | Real |  | Fake |  | Total |  |  | Day | Time
0124988: [T] Master User report is not being generated since 04/08/2025 | 3 | 0 | Mon | 9 | 56 | 11 | 43 | 0124988: [t] master user report is not being generated since 04/08/2025 | 2 | 50 | 0 | 40 | 3 | 30 | 0124988: [t] master user report is not being generated since 04/08/2025 | Mon | 3 | 30
|  |  |  | 11 | 52 | 12 | 55 | 0123707: [t] api > double stripe subscription | 9 | 55 | 5 | 15 | 15 | 10 | 0123707: [t] api > double stripe subscription | Mon | 4 | 30
0123707: [T] Api > Double Stripe Subscription | 13 | 0 |  | 13 | 45 | 17 | 0 | team meeting | 1 | 25 | 0 | 5 | 1 | 30 | 0123707: [t] api > double stripe subscription | Tue | 8 | 0
|  |  | Tue | 9 | 40 | 10 | 45 | 0125030: [t] admin > sentry >ai student agent | 2 | 55 | 1 | 45 | 4 | 40 | 0123707: [t] api > double stripe subscription | Wed | 2 | 40
|  |  |  | 10 | 59 | 11 | 33 | 0123685: [ncp] wrong loading implementation | 5 | 25 | 1 | 35 | 7 | 0 | team meeting | Wed | 1 | 30
|  |  |  | 11 | 41 | 13 | 41 | 0124445: [t][tm] mobile > modify question view to allow question text with tags | 6 | 10 | 0 | 50 | 7 | 0 | 0125030: [t] admin > sentry >ai student agent | Wed | 3 | 50
|  |  |  | 14 | 15 | 14 | 30 | 0124910: [t] chapters deleted with non-deleted questions | 0 | 30 | 0 | 40 | 1 | 10 | 0125030: [t] admin > sentry >ai student agent | Thu | 0 | 50
Team meeting | 1 | 15 |  | 14 | 30 | 15 | 55 | TOTAL | 29 | 10 | 10 | 50 | 40 | 0 | 0123685: [ncp] wrong loading implementation | Thu | 7 | 0
0123707: [T] Api > Double Stripe Subscription |  |  |  | 16 | 11 | 17 | 7 | [7 empty] | 0124445: [t][tm] mobile > modify question view to allow question text with tags | Thu | 0 | 10
|  |  | Wed | 10 | 45 | 12 | 35 | [7 empty] | 0124445: [t][tm] mobile > modify question view to allow question text with tags | Fri | 6 | 50
0125030: [T] Admin > Sentry >AI student agent | 4 | 0 |  | 12 | 48 | 14 | 0 | [7 empty] | 0124910: [t] chapters deleted with non-deleted questions | Fri | 1 | 10
|  |  |  | 14 | 40 | 15 | 47 | [7 empty] | TOTAL | Mon-Fri | 40 | 0
|  |  |  | 16 | 3 | 16 | 41
0123685: [NCP] Wrong loading implementation | 6 | 0 |  | 16 | 58 | 17 | 55
|  |  | Thu | 10 | 4 | 13 | 7
|  |  |  | 13 | 50 | 14 | 30
|  |  |  | 14 | 47 | 15 | 20
0124445: [T][TM] Mobile > Modify question view to allow question text with tags |  |  |  | 15 | 40 | 17 | 10
0123685: [NCP] Wrong loading implementation |  |  | Fri | 9 | 20 | 9 | 30
0124445: [T][TM] Mobile > Modify question view to allow question text with tags | 6 | 0 |  | 9 | 39 | 12 | 30
|  |  |  | 13 | 58 | 15 | 47
0124910: [T] Chapters deleted with non-deleted questions | 1 | 0 |  | 16 | 13 | 16 | 41
Compute
Reset

## Tracking-Week18-2025
TODO: export historical tracking data with one button
Input | [7 empty] | Output: balancing summary | [6 empty] | Output: distributed across days
Ticket |  |  | Timestamp |  |  |  |  | Ticket | Time | [5 empty] | Ticket | Tracker
Name | E |  | Day | Start |  | End |  |  | Real |  | Fake |  | Total |  |  | Day | Time
0124910: [T] Chapters deleted with non-deleted questions | 5 | 0 | Mon | 10 | 4 | 11 | 4 | 0124910: [t] chapters deleted with non-deleted questions | 4 | 25 | 1 | 50 | 6 | 15 | 0124910: [t] chapters deleted with non-deleted questions | Mon | 6 | 20
|  |  |  | 11 | 13 | 12 | 20 | 0124994: [t] review question statuses behavior | 3 | 55 | 1 | 10 | 5 | 5 | 0124994: [t] review question statuses behavior | Mon | 1 | 40
|  |  |  | 12 | 30 | 12 | 50 | 0124446: [t][tm] mobile > modify further reading view to allow question with tags | 3 | 35 | 5 | 15 | 8 | 50 | 0124994: [t] review question statuses behavior | Tue | 3 | 20
|  |  |  | 13 | 54 | 14 | 25 | team meeting | 1 | 5 | 0 | -5 | 1 | 0 | 0124446: [t][tm] mobile > modify further reading view to allow question with tags | Tue | 4 | 40
|  |  |  | 14 | 35 | 16 | 4 | 0123746: [t] intercom > mobile > internal server error | 7 | 20 | 1 | 35 | 8 | 55 | 0124446: [t][tm] mobile > modify further reading view to allow question with tags | Wed | 4 | 10
0124994: [T] Review question statuses behavior |  |  |  | 16 | 30 | 17 | 20 | 0118649: [t] api > investigate and optimize frequently used endpoints | 1 | 20 | 0 | 35 | 1 | 55 | team meeting | Wed | 1 | 0
|  |  | Tue | 9 | 58 | 11 | 54 | TOTAL | 21 | 40 | 10 | 20 | 32 | 0 | 0123746: [t] intercom > mobile > internal server error | Wed | 2 | 45
|  |  |  | 12 | 12 | 12 | 36 | [7 empty] | 0123746: [t] intercom > mobile > internal server error | Fri | 6 | 10
0124446: [T][TM] Mobile > Modify further reading view to allow question with tags | 7 | 0 |  | 13 | 20 | 14 | 18 | [7 empty] | 0118649: [t] api > investigate and optimize frequently used endpoints | Fri | 1 | 50
Team meeting | 0 | 45 |  | 14 | 30 | 15 | 35 | [7 empty] | TOTAL | Mon-Fri | 32 | 0
0124994: [T] Review question statuses behavior | 4 | 0 |  | 15 | 55 | 16 | 40
0124446: [T][TM] Mobile > Modify further reading view to allow question with tags |  |  | Wed | 10 | 46 | 13 | 22
0123746: [T] Intercom > Mobile > Internal Server Error | 7 | 0 |  | 14 | 12 | 15 | 28
|  |  |  | 15 | 44 | 16 | 28
|  |  |  | 16 | 50 | 18 | 6
|  |  | Fri | 9 | 53 | 11 | 25
|  |  |  | 11 | 44 | 12 | 30
|  |  |  | 12 | 35 | 13 | 38
|  |  |  | 14 | 20 | 15 | 3
0118649: [T] API > Investigate and optimize frequently used endpoints | 1 | 30 |  | 15 | 20 | 16 | 40
Compute
Reset

## Tracking-Week19-2025
TODO: export historical tracking data with one button
Input | [7 empty] | Output: balancing summary | [6 empty] | Output: distributed across days
Ticket |  |  | Timestamp |  |  |  |  | Ticket | Time | [5 empty] | Ticket | Tracker
Name | E |  | Day | Start |  | End |  |  | Real |  | Fake |  | Total |  |  | Day | Time
0118649: [T] API > Investigate and optimize frequently used endpoints |  |  | Mon | 11 | 3 | 11 | 15 | 0118649: [t] api > investigate and optimize frequently used endpoints | 0 | 10 | 0 | -10 | 0 | 0 | 0118649: [t] api > investigate and optimize frequently used endpoints | Mon | 0 | 5
0125392: [T] [AS] End of Chapter improvements | 15 | 0 |  | 11 | 16 | 13 | 47 | 0125392: [t] [as] end of chapter improvements | 14 | 35 | 6 | 0 | 20 | 35 | 0125392: [t] [as] end of chapter improvements | Mon | 7 | 55
|  |  |  | 14 | 45 | 17 | 22 | 0125393: [t] [as] sentry > audio study > type error | 3 | 40 | 2 | 30 | 6 | 10 | 0125392: [t] [as] end of chapter improvements | Tue | 8 | 0
|  |  |  | 17 | 34 | 17 | 58 | team meeting | 0 | 45 | 0 | 0 | 0 | 45 | 0125392: [t] [as] end of chapter improvements | Wed | 4 | 40
|  |  | Tue | 9 | 25 | 10 | 45 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | 4 | 35 | 2 | 15 | 6 | 50 | 0125393: [t] [as] sentry > audio study > type error | Wed | 3 | 20
|  |  |  | 10 | 57 | 11 | 51 | 0125545: [ncp] variable no definida. | 3 | 35 | 1 | 55 | 5 | 30 | 0125393: [t] [as] sentry > audio study > type error | Thu | 2 | 55
|  |  |  | 12 | 15 | 12 | 48 | TOTAL | 27 | 20 | 12 | 30 | 39 | 50 | team meeting | Thu | 0 | 45
0125393: [T] [AS] Sentry > Audio Study > Type Error | 4 | 30 |  | 13 | 54 | 14 | 30 | [7 empty] | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Thu | 4 | 20
Team meeting | 0 | 30 |  | 14 | 30 | 15 | 15 | [7 empty] | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Fri | 2 | 35
0125393: [T] [AS] Sentry > Audio Study > Type Error |  |  |  | 15 | 45 | 16 | 15 | [7 empty] | 0125545: [ncp] variable no definida. | Fri | 5 | 25
|  |  |  | 16 | 25 | 17 | 8 | [7 empty] | TOTAL | Mon-Fri | 40 | 0
|  |  | Wed | 10 | 10 | 11 | 13
|  |  |  | 11 | 26 | 11 | 41
|  |  |  | 11 | 47 | 12 | 20
0125392: [T] [AS] End of Chapter improvements |  |  |  | 12 | 21 | 13 | 14
|  |  |  | 14 | 10 | 14 | 48
0125391: [T] [AS] Review and implement 'abbreviations list' more user friendly |  |  |  | 15 | 5 | 17 | 16
0125392: [T] [AS] End of Chapter improvements |  |  | Thu | 9 | 56 | 14 | 0
|  |  |  | 15 | 20 | 16 | 3
0125391: [T] [AS] Review and implement 'abbreviations list' more user friendly |  |  |  | 16 | 20 | 16 | 53
|  |  |  | 17 | 10 | 17 | 20
0125545: [NCP] Variable no definida. | 4 | 0 | Fri | 10 | 25 | 12 | 55
|  |  |  | 14 | 5 | 15 | 10
0125391: [T] [AS] Review and implement 'abbreviations list' more user friendly | 5 | 0 |  | 15 | 32 | 17 | 7
|  |  |  | 17 | 24 | 17 | 32
Compute
Reset

## Tracking-Week20-2025
Input | [7 empty] | Output: balancing summary | [6 empty] | Output: distributed across days
Ticket |  |  | Timestamp |  |  |  |  | Ticket | Time | [5 empty] | Ticket | Tracker
Name | E |  | Day | Start |  | End |  |  | Real |  | Fake |  | Total |  |  | Day | Time
0125391: [T] [AS] Review and implement 'abbreviations list' more user friendly | 13 | 0 | Mon | 10 | 13 | 11 | 42 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | 24 | 40 | 8 | 50 | 33 | 30 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Mon | 8 | 0
|  |  |  | 12 | 5 | 13 | 39 | 0124910: [t] chapters deleted with non-deleted questions | 1 | 45 | 3 | 5 | 4 | 50 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Tue | 8 | 0
|  |  |  | 14 | 35 | 15 | 32 | 0125392: [t] [as] end of chapter improvements | 0 | 15 | 0 | -5 | 0 | 10 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Wed | 8 | 0
0124910: [T] Chapters deleted with non-deleted questions | 2 | 30 |  | 15 | 48 | 17 | 33 | team meeting | 1 | 25 | 0 | 5 | 1 | 30 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Thu | 8 | 0
0125392: [T] [AS] End of Chapter improvements |  |  | Tue | 9 | 41 | 9 | 57 | TOTAL | 28 | 5 | 11 | 55 | 40 | 0 | 0125391: [t] [as] review and implement 'abbreviations list' more user friendly | Fri | 1 | 30
0125391: [T] [AS] Review and implement 'abbreviations list' more user friendly |  |  |  | 10 | 9 | 10 | 49 | [7 empty] | 0124910: [t] chapters deleted with non-deleted questions | Fri | 4 | 50
|  |  |  | 11 | 0 | 12 | 15 | [7 empty] | 0125392: [t] [as] end of chapter improvements | Fri | 0 | 10
|  |  |  | 12 | 30 | 13 | 45 | [7 empty] | team meeting | Fri | 1 | 30
|  |  |  | 14 | 40 | 14 | 53 | [7 empty] | TOTAL | Mon-Fri | 40 | 0
Team meeting | 0 | 25 |  | 14 | 55 | 16 | 22
0125391: [T] [AS] Review and implement 'abbreviations list' more user friendly |  |  |  | 16 | 44 | 17 | 10
|  |  | Wed | 10 | 30 | 13 | 10
|  |  |  | 14 | 0 | 15 | 38
|  |  |  | 16 | 1 | 16 | 36
|  |  |  | 16 | 45 | 17 | 30
|  |  |  | 17 | 44 | 18 | 0
|  |  | Thu | 9 | 50 | 11 | 15
|  |  |  | 11 | 26 | 12 | 14
|  |  |  | 12 | 25 | 13 | 42
|  |  |  | 14 | 33 | 16 | 25
|  |  | Fri | 10 | 5 | 12 | 5
|  |  |  | 12 | 23 | 13 | 39
|  |  |  | 14 | 30 | 15 | 47
|  |  |  | 16 | 8 | 17 | 10
Compute
Reset